## Perm Rule Filing date Calculate
PERMANENT RULEMAKING CALCULATOR See Instructions worksheet for screenreader instructions.
As of Jan 1, 2010 the Colorado Register will publish twice per month, on the 10th and the 25th
Enter Desired Effective Date |  |  |  | Enter Hearing Notice Filing Date
to view suggested rulemaking timeline |  |  |  | to view suggested rulemaking timeline
2024-09-23
| M M / D D / Y Y Y Y |  |  |  | M M / D D / Y Y Y Y
You may need to adopt Emergency Rules
to achieve desired effective date*
File Notice on
| or before: |  |  |  | Notice Filed:
| 2024-06-15 | B44 is B49 - 10 days (pub d-line)
| Notice Published in |  |  |  | Notice Published in
| Colorado Register: |  |  |  | Colorado Register:
| 2024-06-25 | B18 is closest Pub date prior to B19
| 2024-06-26 | B19 is B24 - 20 days
| Hold Hearing on |  |  |  | Hold Hearing on
| or after: |  |  |  | or after:
| 2024-07-15 | B23 is B18(Ntc Pub date) +20
| 2024-07-16 | B24 is B28(Adop Date) - 20 days
| Adopt Rules on | Enter Actual |  |  | Adopt Rules on | Enter Actual
| or before: | Adoption Date: |  |  | or before: | Adoption Date:
2024-07-26
| to ensure eff date: | M M / D D / Y Y Y Y |  |  | to ensure eff date: | M M / D D / Y Y Y Y
| 2024-09-23 | B28 is B44 - 20 days (for AGO)
| Request AG | Request AG |  |  | Request AG | Request AG
| Opinion by: | Opinion by: |  |  | Opinion by: | Opinion by:
2024-07-27
B34 is B28 + 1
| AG Issues | AG Issues | Enter Actual |  | AG Issues | AG Issues | Enter Actual
| Opinion by: | Opinion by: | AG Opinion Date: |  | Opinion by: | Opinion by: | AG Opinion Date:
2024-08-15
|  |  | M M / D D / Y Y Y Y |  |  |  | M M / D D / Y Y Y Y
B39 is B44
| File Rules on | (full 20 days) |  |  | File Rules on
| or before: |  |  |  | or before:
2024-08-15
B44 is B49 - 10 days (pub d-line)
B44 is also last day of 20 day d-line
| Rules Published |  |  |  | Rules Published
| in Register: |  |  |  | in Register:
2024-08-25
| 2024-09-03 | B50 is Desired Eff Date - 20 days
B49 is closest Pub date prior to B50
| Earliest Possible |  |  |  | Earliest Possible
| Effective Date: |  |  |  | Effective Date:
2024-09-14
* Dates generated are suggestions, allowing extra time for hearings, and 20 days for AG Opinions. Enter Actual (or other alternative)
dates for these variables to see how the Effective Date may be changed. Please call with questions.
Colorado Secretary of State • Administrative Rules Program • 1700 Broadway, Suite 300 • Denver CO 80290 • 303-894-2200 • www.sos.state.co.us
OR

## Screen Reader Instructions
To use this calculator enter either a desired Effective Date or Date of Hearing Notice Filing Date. The sheet uses Data Validation to identify six data entry fields. Use the Tab Key to navigate between them. Once on a data entry field enter a value and arrow down for calculated results.